## Use Case 1
Use Case 1: Home Page
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
UC1-1 | User is not logged in | Verify the "Home Page" | 1. Open the application URL | The home page is displayed with Home Page, Navigation bar and Carousel | Pass
UC1-2 | User is not logged in | Verify the "Navigation bar" | 1. Open the application URL | The following button/links are present: -SIGN UP -LOG IN | Pass
UC1-3 | User is not logged in | Verify the "Carousel" | 1. Open the application URL | Verify the carousel display the following three sections: -Summarize the story -Upload a pictures -Ready to spoil a story | Pass
UC1-4 | User is not logged in | Verify "SIGN UP" button from Navigation bar | 1. Open the application URL 2. Click on SIGN UP button from upper-right part in the NavBar | SIGN UP page is loaded | Pass
UC1-5 | User is not logged in | Verify "LOG IN" button from Navigation bar | 1. Open the application URL 2. Click on LOG IN button from upper-right part in the NavBar | LOG IN page is loaded | Pass
UC1-6 | User is not logged in | Verify "Copyright Footer" is working | 1. Open the application URL 2. Scrow down to "Copyright Footer" 3. Click on "StorySpoil" button | Then StorySpoil button is clicked it leads to copyrightpage wich includes (name of owner, year of copyright and other) | Fail | Bug - 4
* If you want to add a new line in a cell, use Alt + Enter

## Use Case 2
Use Case 2: User Registration
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
UC2-1 | User is not logged in | Verify "SIGN UP" labels and buttons | 1. Open the application URL 2. Click on "SIGN UP" button | The following labels are present: -Username -Email -First Name -Middle Name -Last Name -Password -Confirm Password -"SIGN UP" button -"LOG IN HERE" button | Pass
UC2-2 | User is not logged in | Verify the field length | 1. Open the application URL 2. Click on "SIGN UP" button 3. Try to enter: -more than 30 symbols in Username field -more than 254 in Email field -more than 60 characters in First/Middle/Last Name field -more than 30 characters in Password field -more than 30 characters in Confirm Password field | User should not be able to enter more symbols than the specified one | Pass
UC2-3 | User is not logged in | Verify registration with Username below the lower boundary | 1. Open the application 2. Click on "SIGN UP" button 3. Enter -Username -"P" -Email - "testivan@test.com" -First/Middle/Last name - "Ivan"/"Nankov"/"Nikolov" -Password - "123456" -Confirm Password - "123456" | Validation message for Username should appears | Pass
UC2-4 | User is not logged in | Verify registration with Username on the lower boundary | 1. Open the application 2. Click on "SIGN UP" button 3. Enter -Username -"XO" -Email - "nikolov@test.com" -First/Middle/Last name - "Ivan"/"Nankov"/"Nikolov" -Password - "123456" -Confirm Password - "123456" | User is successfully registered | Pass
UC2-5 | User is not logged in | Verify registration with Username on the upper boundary | 1. Open the application 2. Click on "SIGN UP" button 3. Enter -Username -"xoxoxoxoxoxoxoxoxoxoxoxoxoxoxo" -Email - "nikolovi@test.com" -First/Middle/Last name - "Ivan"/"Nankov"/"Nikolov" -Password - "123456" -Confirm Password - "123456" | User is successfully registered | Pass

## Use Case 3
Use Case 3: User Sign In
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
UC3-1 | User is not logged in | Verify "LOG IN" labels and buttons | 1. Open the application URL 2. Click on "LOG IN" button | The following labels are present: -Username -Password -"LOG IN" button -"Forgot Password?" -"CREATE NEW" button | Pass
UC3-2 | With user "XO" | Login with valid username and password | 1. Open the application URL 2. Click on "LOG IN" button 3. Enter: -Username - "XO" -Password - "123456" | User is logged in | Pass
UC3-3 | With wrong username | Login with valid username and correct password | 1. Open the application URL 2. Click on "LOG IN" button 3. Enter: -Username - "X1O" -Password - "123456" | User is not logged in | Pass

## Use Case 4
Use Case 4: Profile Management
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
UC4-1 | User "nikolov@test.com" is registered. User does not have any spoilers yet | Verify my profil page labels | 1. Login with "nikolov@test.com" 2. Click on "My Profile" link | Verify the following state of the form: -default empty profile picture is shown -"Edit" profile button is present -Username/Full name and Email are present -Spoler counter equal to 0 -"About me" information -"Create Spoiler" button is present -"Logout" button is present | Pass |  | Priority options: | 1. Blocker
UC4-2 | User "nikolov@test.com" is registered. | Verify "Logout" button is working | 1. Login with "nikolov@test.com" 2. Click on "My Profile" link 3. Click on "Logout" button | User should be no longer logged in. | Pass |  |  | 2. High
3. Medium
4. Low

## Use Case 5
Use Case 5: Spoiler Creation
Test Case ID | Prerequisites | Description | Steps | Expected result: | Pass / Fail | Comments
UC5-1 | User "nikolov@test.com" is registered. | Verify required fields | 1. Login with "nikolov@test.com" 2. Click on "Write Spoiler" 3. Click on "CREATE" | Validation message for empty title and description should appears | Pass
UC5-2 | User "nikolov@test.com" is registered. | Verify required fields | 1. Login with "nikolov@test.com" 2. Click on "Write Spoiler" 3. Enter: -Story title - "Once upon a time" -Describe your story spoiler - "Bulgaria" -Add a pictures for the spoiler - "not required" 4. Click on "CREATE" | The story spoiler is created | Pass

## Use Case 6
Use Case 6: Spoiler Management
Test Case ID | Prerequisites | Description | Steps | Expected result: | Pass / Fail | Comments
UC6-1 | User "ivann@test.com" is registered. User does not have any spoilers yet | Verify the message when no spoiler are displayed | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "ivann@test.com" | Message "No Spoilers Yes" is displayed | Pass
UC6-2 | User "nikolov@test.com" is registered. | Verify user is able to see all spoilers | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "nikolov@test.com" | All the user spoilers are listed | Pass
UC6-3 | User "nikolov@test.com" is registered. | Verify user is able to Share spoilers | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "nikolov@test.com" | The spoiler can not be shared | Fail | Bug - 7
UC6-4 | User "nikolov@test.com" is registered. | Verify user is able to Edit spoilers | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "nikolov@test.com" | The spoiler is edited | Pass
UC6-5 | User "nikolov@test.com" is registered. | Verify user is able to Delete spoilers | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "nikolov@test.com" | The spoiler is deleted | Pass

## BUG REPORT
Bug Report
Bug ID | Test Case ID | Priority | Severity | Title | Steps to reproduce | Expected result | Actual result | Comments
1 | UC1-3 | High | High | Missing picture on the second section promoting The App Exp. | 1. Open the application 2. Scroll down to the three promoting section | There should be three corresponding pictures with short description and motivational phrase | The second corresponding picture is missing
2 | UC1-3 | Medium | Medium | Missing thumbnails (little pictures) in all of the three promoting sections | 1. Open the application 2. Scroll down to the three promoting section | There should be thumbnails in all of the three promoting sections | Thumbnails are missing
3 | UC1-3 | Low | Low | Missing emoticons in short description in the all three promoting sections | 1. Open the application 2. Scroll down to the three promoting section | There should be emoticons in the short description of all three promoting sections | Emoticons are missing in all three promoting sections
4 | UC1-6 | Medium | Medium | Copyright footer does not working | 1. Open the application 2. Scroll down 3. Click on StorySpoil button | Then StorySpoil button is clicked it leads to copyrightpage wich includes (name of owner, year of copyright and other) | Then StorySpoil button is clicked it leads to Home page
5 | UC2-1 | Low | Low | Missing emoticons in "Join us" description after "SIGN UP" button is clicked | 1. Open the application 2. Click on "SIGN UP" button | There should be "Join us" descripton with emoticons. | Emoticons in description are missing after "SIGN UP" button is clicked
6 | UC3-1 | Low | Low | Missing emoticons in "Welcome back to StorySpoil" description after "LOG IN" button is clicked | 1. Open the application 2. Click on "LOG IN" button | There should be "Welcome back to StorySpoil" descripton with emoticons. | Emoticons in description are missing after "LOG IN" button is clicked
7 | UC6-3 | High | Critical | "Share" option button is missing | 1. Open the application URL 2. Click on "LOG IN" button 3. Login with "nikolov@test.com" | There should be three option buttons Share, Edit and Delete | "Share" button does not exist